## Project schedule
|  | Grocery-Web-App | [5 empty] | Project start: | [7 empty] | 2025-06-01
|  | Akshit Dhake | [5 empty] | Display week: | [7 empty] | 2
|  | Avishkar Pawar | Project
|  | Arya | Members
Shurti
[8 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28
|  | TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-06-09 to 2025-08-03
 | time axis 2025-06-09 to 2025-08-03
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Expected | Requirement Analysis and Planning
|  | Gather and Document project requirements | All | 100% | 2025-06-01 | 2025-06-01 | 1
|  | Gantt Chart | Akshit | 100% | 2025-06-01 | 2025-06-01 | 1
|  | Raci | Shruti | 100% | 2025-06-01 | 2025-06-01 | 1
|  | Wire-frames | Arya, Avshikar | 100% | 2025-06-01 | 2025-06-01 | 1
| Actual | Requirement Analysis and Planning
|  | Gather and Document project requirements | All | 100% | 2025-06-02 | 2025-06-05 | 4
|  | Gantt Chart | Akshit | 100% | 2025-06-05 | 2025-06-05 | 1
|  | Raci | Shruti | 100% | 2025-06-05 | 2025-06-06 | 2
|  | Wire-frames | Arya, Avshikar | 100% | 2025-06-01 | 2025-06-01 | 1
| Expected | Database Design and API Development
|  | Design database schema | Arya,Avishkar | 100% | 2025-06-02 | 2025-06-03 | 2
|  | Setup middleware & API structure | Akshit | 100% | 2025-06-03 | 2025-06-03 | 1
|  | Develop API endpoints | Aavshikar | 100% | 2025-06-04 | 2025-06-07 | 4
|  | Perform API testing using Postman | Shruti | 100% | 2025-06-04 | 2025-06-08
| Actual | Database Design and API Development
|  | Design database schema | Arya,Avishkar | 100% | 2025-06-07 | 2025-06-08 | 2
|  | Setup middleware and API structure | Akshit | 100% | 2025-06-08 | 2025-06-09 | 2
|  | Develop API endpoints | Aavshikar | 100% | 2025-06-08 | 2025-06-11 | 4
|  | Perform API testing using Postman | Shruti | 100% | 2025-06-08 | 2025-06-10
| Expected | UI Development and API Integration
|  | Login,Signup,Otp | Akshit | 100% | 2025-06-09 | 2025-06-10 | 2
|  | Buyer Dashboard And Profile | Akshit | 100% | 2025-06-09 | 2025-06-11
|  | BuyerOrder | Akshit | 100% | 2025-06-11 | 2025-06-13
|  | Seller Dashboard | Shruti | 100% | 2025-06-09 | 2025-06-11 | 3
|  | Seller Quatation | Shruti | 100% | 2025-06-11 | 2025-06-13
|  | Seller analytics | Shruti | 100% | 2025-06-13 | 2025-06-15 | 3
|  | Chat System | Arya, Avishkar | 100% | 2025-06-09 | 2025-06-12 | 4
|  | Admin Dashboard | Arya, Avishkar | 100% | 2025-06-13 | 2025-06-15 | 3
| Actual | UI Development and API Integration
|  | Login,Signup,Otp | Akshit | 100% | 2025-06-10 | 2025-07-10 | 31
|  | Buyer Dashboard And Profile | Akshit | 100% | 2025-06-08 | 2025-07-15 | 38
|  | BuyerOrder | Akshit | 100% | 2025-06-08 | 2025-07-15 | 38
|  | Seller Dashboard | Shruti | 100% | 2025-06-08 | 2025-07-15
|  | Seller Quatation | Shruti | 100% | 2025-06-09 | 2025-07-17
|  | Seller analytics | Shruti | 100% | 2025-06-09 | 2025-07-15
|  | Chat System | Arya, Avishkar | 100% | 2025-06-10 | 2025-07-20
|  | Admin Dashboard | Arya, Avishkar | 100% | 2025-06-11 | 2025-07-20 | 40
| Expected | Testing and Debugging
|  | Perform Blackbox testing | Prathamesh,Srivaths Iyer | 100% | 2025-06-16 | 2025-06-17 | 2
|  | Fix bugs and optimize performance | Full Team | 100% | 2025-06-16 | 2025-06-17 | 2
| Actual | Testing and Debugging
|  | Perform Blackbox testing | Prathamesh,Srivaths Iyer | 100% | 2025-07-25 | 2025-07-26
|  | Fix bugs and optimize performance | Full Team | 100% | 2025-07-25 | 2025-07-25 | 1
| Expected | Deployment and Final Review
|  | Setup Php MyAdmin | Akshit | 100% | 2025-06-18 | 2025-06-19 | 2
|  | Setup Php node App | Akshit | 100% | 2025-06-18 | 2025-06-19
|  | Monitor a | Arya | 100% | 2025-06-19 | 2025-06-19 | 1
|  | Finalk documentattion | Arya Shruti | 100% | 2025-06-18 | 2025-06-20 | 3
| Actual | Deployment and Final Review
|  | Setup Php MyAdmin | Akshit | 100% | 2025-07-21 | 2025-07-21 | 1
|  | Setup Php node App | Akshit | 100% | 2025-07-21 | 2025-07-21 | 1
|  | Monitor a | Arya | 100% | 2025-07-21 | 2025-07-21
|  | Finalk documentattion | Arya Shruti | 100% | 2025-07-25 | 2025-07-25